## Project Plan and Gantt
Project Name | Ứng dụng quản lý Sinh Viên
Project Manager | Đỗ Minh Thịnh
Start Date | 2016-09-10
End Date | 2016-10-11
Overall Progress | 10%
Tasks | Responsible | Start | End | Days | Status
Lên kế hoạch | Đỗ Minh Thịnh | 2016-09-10 | 2016-09-15 | 5 | Complete
Thu thập yêu cầu | Võ Trường Thi | 2016-09-11 | 2015-09-07 | 4 | Overdue
Phân tích thiết kế hệ thống | Đỗ Minh Thịnh,Võ Trường Thi | 2016-09-11 | 2016-09-18 | 7 | In progress
Thiết kế database | Đỗ Minh Thịnh | 2016-09-19 | 2016-09-22 | 4 | Not started
Code view | Võ Trường Thi | 2016-09-23 | 2016-10-05 | 13 | Not started
Code model | Đỗ Minh Thịnh | 2016-09-23 | 2016-10-05 | 13 | Not started
Code controller | Võ Trường Thi | 2016-09-23 | 2016-10-05 | 13 | Not started
Demo | Đỗ Minh Thịnh | 2016-10-06 | 2016-10-06 | 0 | Not started
Fix Bug | Võ Trường Thi | 2016-10-07 | 2016-10-10 | 4 | Not started
Launch | Đỗ Minh Thịnh,Võ Trường Thi | 2016-10-11 | 2016-10-11 | 1

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address | Requirements | Expectations
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team